Town of Orangetown

Climate Smart Community Mtg - Meeting Minutes

Date: 		Friday November 19th, 2021. 11 am

Location: 	Town Hall – Court Room #1

Attendees: 	Eamon Reilly, Commissioner DEME/Committee Chair (ER)

Maria Gagliardi (MG)		Allison Kardon (AK)			Mike Andrea (MA)

Jane Slavin (JS)			Christopher Sheehan (CS)

Discussion Topics:

- Orangetown current Point accumulation review.  (AK) compiled/will submit list.

- The need to have a representative from the Highway Dept attend/be a part of this committee.

- Completed efforts: 1.2, 1.3, 3.15, 3.2, 3.4, Stretch, 6.3, 6.11,

- Review of Greenhouse gas points – compared to other Villages that have successfully achieved points. (PE2.1 & 2.2) (MA)

- Review of potential tasks to achieve additional points;

  - 3.2 LED lighting – in process.

  - 3.4 sink fixtures for Water Efficiency. In process

  - 3.8/3.9 Fleet inventory – Need to collect/ re-submit

  - 3.1.5 Street lights – Completed. Need to submit.

  - Traffic light conversion (ask Highway)

  - Other completed projects that may be included

    - Solar Code Updated/completed, recycle bins distributed, St Pats recycle event, Farmers’ Mrkt, E-car recharging stations.

  - 5.11 – Food recycle kits & set up drop off area – Communicate to public.  (AK/Hwy)

  - 7.15 – Flood Insurance initiative.  Research possibilities. (JS)

  - 5.13 – Waste reduction campaign (Marcy)

- Possible priorities   3.1, 2.2, 6.11, 6.9.

- Need Pledge element.

Action Items:

- 3.2 – T. Kenny to draft letter.

- Attainment of Greenhouse Gas points.  MA to write up & present to AK.

- ER/Hwy/Parks to create a building list to assess LED lighting potential.

  - ER called/emailed Dept Heads 04/27/21. -  In Process – Needs completion

- ER/Hwy/Parks to create fixture list to assess Water Efficiency potential.

  - ER called/emailed Dept Heads 04/27/21.  In Process – Needs completion

- Dept Heads to report Fleet Inventory. AK to submit.

- AK/Hwy to review Food Recycle location & Bike Trails- 6.10..

- Carmel Reilly - Farmers’ Market – Identify if we are to have it this year; AK to submit.

- MA/MG/AK/Hwy (6.14) to draft project list that can be used for Traffic Calming credit/points; Mountainview Ave, Oaktree Rd, sidewalks, new striping, ect.

- 3.16 – LED traffic lights – Need update from Highway.

- 6.1 – Sustainability Plan – TK/AK/JS working on it.

- 7.21 – ER to follow up w/ Highway – Innovative Plastics Culvert, ect

- ER/JS get remediation into & establish Brown Site.

- 9.4/9.5 – TK/AK/MA – Keep up Newsletters & Social Media updates for compliance.

- 6.11 - Electrical Vehicle recharging stations. Completed.  To be repaired & re-submitted. AK

- AK to research Pledge Elements – Committee to Identify ours